## Slide 1
29.04.2025
Dr. Tarja Dworrak, Centre for Research and Knowledge Transfer
International Research Management
Project Management and Financial Procedures

## Slide 2
Within the Erasmus+ Programmes
Weihenstephan-Triesdorf University of Applied Sciences | Agri-Mocks
Extending the reach
Technology-enabled learning across cultures
 Inclusive and accessible internationalization strategies
 Contribution to the digital transformation of higher education
Capacities for digital pedagogy and global networking
Institutional goals for internationalization
Notes: Virtual exchange compliments the traditional mobility of Erasmus+ and extends the reach
VE = technology-enabled, people-to-people dialogues and collaborative learning across cultures
Goals:
Inclusive and accessible internationalization strategies
Contribution to the digital transformation of higher education and youth work
Benefits:
Expand international collaboration without high logistical or financial effort
Align with institutional goals for diversity, inclusion, and internationalization
Build capacities for digital pedagogy and global networking.

## Slide 3
Governance Structure EU Funded Projects
Weihenstephan-Triesdorf University of Applied Sciences | Agri-Mocks
Grant Agreement (GA) = consortium + European Commission
Consortium Agreement (CA) = between the consortium
External obligations
Internal obligations
Notes: 1. Grant Agreement (GA)
Between the EC and the Coordinator (on behalf of the consortium)
Legal contract setting out the rules of the Erasmus+ funding
Defines:
  Overall project scope, objectives, and budget
  Eligibility rules and reporting requirements
  Payment structure (Lump Sum model in this case)
The coordinator is legally responsible for:
  Communicating with the EC
  Submitting reports
  Distributing funds to partners based on implementation
2. Consortium Agreement (CA)
Between all project partners – internal governance
Defines how the consortium will work together
Customizable – adapted to project size and complexity
Specifies:
  Partner roles and responsibilities
  Decision-making processes (e.g. voting rules)
  Internal communication and reporting procedures
  Conflict resolution and liability clauses
  Distribution of lump sum shares (who gets what, when)

## Slide 4
Lump Sum Funding Model
Weihenstephan-Triesdorf University of Applied Sciences | Agri-Mocks
WP
WP
WP
Deliverable
Deliverable
Deliverable
Deliverable
Deliverable
Deliverable
Deliverable
Deliverable
Deliverable
Notes: How it Works
The grant is broken into work packages or activities
Each work package is linked to:
  Expected results or deliverables
  A fixed amount of funding
Funds are paid if the results are delivered and accepted → If not, that part of the lump sum may be reduced or rejected
Reporting Under Lump Sum
Focuses on what was done, not how much it cost
You must prove implementation, e.g.:
  Participation records
  Meeting reports or recordings
  Learning content, videos, screenshots, publications
No financial documents (invoices, payslips, etc.) are submitted to the EC
Implications for Partners
Each partner is responsible for:
  Implementing agreed activities
  Providing evidence of delivery
Internal payments (from coordinator to partners) are often linked to milestones
Your share of the lump sum is defined in the Consortium Agreement
The estimated lump sum breakdown does not prescribe how the EU contribution is to be used by the beneficiaries. It shows the amounts that the EACEA commits to pay if the action is implemented properly, regardless of the costs actualy incurred.

## Slide 5
Lump Sum Funding Model: Assessing WP
Weihenstephan-Triesdorf University of Applied Sciences | Agri-Mocks
Activities carried out
Quality of the deliverables
Achievement of the objectives and expected outcomes
 WP Completed vs. Not Completed
All taks/deliverables completed Or Equivalent tasks reaching the same result All partners completed it Deviations: are justified | Can be finished and declared later on in any subsequent report Partially completed: show the % of completion Explanation in the final report

## Slide 6
Lump Sum Funding Model: WP Costs per Partner
Weihenstephan-Triesdorf University of Applied Sciences | Agri-Mocks
Deliverable
Deliverable
Deliverable
Deliverable
Deliverable
Deliverable
Deliverable
Deliverable
Deliverable
Notes: Screenshot from the Portal

## Slide 7
Roles and Responsibilities
Weihenstephan-Triesdorf University of Applied Sciences | Agri-Mocks
Communicate
Coordinator
EU
Project Partners
Share updates, inform the coordinator in case of delays, changes, or risks
Notes: Coordinator (Weihenstephan-Triesdorf University)
Main contact with the EC
Legally responsible for the Grant Agreement
Coordinates overall project activities and quality assurance
Submits progress and final reports
Collects and validates deliverables from partners
Distributes lump sum shares according to the Consortium Agreement
Organises meetings and supports communication
Does the continuous reporting
Project Partners
Carry out the activities assigned in the application and Consortium Agreement
Ensure quality and timely delivery of outputs and milestones
Provide evidence of implementation (photos, agendas, materials, participation logs, etc.)
Share updates and progress with the coordinator
Participate actively in project meetings and collaborative tasks
Inform the coordinator in case of delays, changes, or risks

## Slide 8
Project Timeline and Milestones
Weihenstephan-Triesdorf University of Applied Sciences | Agri-Mocks
Begin 1.2.25
End 1st Period: 31.7.26
Deadline 1. Report:
29.9.26
Begin 1.8.26
End 2nd Period: 31.1.28
Deadline 2. Report:
31.3.28
Sent 40% of the budget
Check, send 40% of the budget
Check, send final payment
Continuous Reporting Portal: Deliverables should be regularly uploaded in the portal before the reporting deadline.
Notes: For additional prefinancings (if any), the amount due, schedule and modalities are also set out in
the Data Sheet (see Point 4.2). However, if the statement on the use of the previous prefinancing
payment shows that less than 70% was used, the amount set out in the Data Sheet will be reduced by
the difference between the 70% threshold and the amount used.
VERY IMPORTANT: Deliverables should be regularly uploaded in the portal before the reporting deadline.
Continuous Reporting = periodic uploading of results
Periodic Reporting Module = linked to payment

## Slide 9
Q&A
Weihenstephan-Triesdorf University of Applied Sciences | Agri-Mocks
?
!
Notes: Further communication

## Slide 10
Thank you for your interest.
Dr. Tarja Dworrak
29.04.2025