# Framework Draft – E-Internship Programme

- Duration: 6 weeks

- Methodology:

  - Track 1 (Learning & Inputs): self-paced MOOC + mentor-led sessions (career, intercultural, civic, innovation). How do we assign and train mentors? We need to consider the mentors' digital literacy, educational background, and field of study.

  - Track 2 (Company Play): students/youth form “virtual companies,” guided by mentors and entrepreneurs, working on real-life tasks. must be delivered by someone with the experience with simulation program like  Capsim

- Final Simulation: 3-day intensive “company capstone” where teams solve a complex challenge from an African entrepreneur.

- Outcome: participants understand how companies work, what roles exist, how decisions are made, and practice collaboration in a real-world inspired context.

### A. Curriculum

- MOOC Modules: can we include Entrepreneurial  Mindset, design thinking or design your venture ( business, prototype, product development)  content to this module ( Business planning, entrepreneurship ( Behavioral aspect of entrepreneurship), project development, climate-resilient agriculture, sustainability & SDGs. : must be based on the context of the country ( Context based)

- Mentor-led sessions: self-awareness, civic participation, innovation, intercultural teamwork, career guidance.

- Company Play (parallel to inputs): role-play as “employees” in a virtual company environment. Each input session feeds into company practice.

### B. Company Play

### Runs throughout Weeks 2–5 in parallel with mentor sessions. (session that needs to completed in parallel with the company-play must be identified and structured)

- Structure:

  - Entrepreneur provides company setting & real-life problem(s).

  - Participants split into functional teams (marketing, R&D, finance, HR, operations, sustainability, advocacy, etc.):

  - Weekly tasks linked to mentor sessions:

    - Example: after a session on civic participation, company teams design a CSR/advocacy initiative.

    - After business planning input, teams draft a mini-business plan.

- Output: evolving portfolio of company deliverables that feed into final simulation.

### C. Simulation Component (Capstone)

- 3-Day Intensive Company Simulation at the end of Week 6. ( how many hour per day?)

- Teams apply knowledge (from MOOCs) and experience (from company play) in a virtual company simulation provided by BizMetrics.

D. Competition

- Community Projects: developed in parallel (Weeks 4–6).

- Competitions:

  - National level: showcase best local projects.

  - International level: top projects compete across countries.

### E. Recognition

- Digital certificates & badges.

- Peer and mentor and entrepreneur feedback.

- Optional academic credit (ECTS alignment). It doesn’t work in EDI context

### F. Virtual Space & Webinars

- Virtual Co-working Platform:

  - Virtual company mode for student internship.

  - Virtual office mode for youth internship.

- Webinars: kick-off debate, midpoint intercultural exchange, final evaluation/reflection.

## Proposed Course Outline (6 Weeks)

### Week 1 – Foundations

- Kick-off webinar & debate.

- Introduction to MOOC module 1:  Business Planning Basics (Business Model Canvas): This topic is suitable for individuals who already have a concept in mind. However, if they do not, the modules should be designed to help them generate a business idea. (Idea generation in Agriculture sectors)

- Mentor sessions: e.g. self-awareness, how to apply for a job, intercultural exchange. (The topic should align with the themes mentioned above)

- ( Company Play: team setup, role assignments (e.g. job descriptions, job interviews, introduction to entrepreneur & company case.

### Week 2 – Business & Innovation

- Introduction to MOOC module 2: Entrepreneurship in Rural Development. ( content of the modules should be identified)

- Mentor session: innovation & global teamwork. ( The topics should must align Entrepreneurship in Rural Development.)

- Company Play: draft first company strategy (linked to MOOC learning).

### Week 3 – Civic Participation & Advocacy

- Introduction to MOOC module 3: Sustainability & SDGs.

- Mentor session: civic participation & leadership.

- Company Play: teams design advocacy or CSR initiative.

### Week 4 – Project Development & Electives

- MOOC module 4: Project Design & Funding.

- Electives (0.5 week, self-paced).

- Mentor session: career guidance & innovation.

- Company Play: apply funding/project design principles to company product or service.

### Week 5 – Integration & Preparation

- Mentor session: simulation preparation.

- Community project development (climate focus).

- Company Play: finalise company outputs, present progress to entrepreneur for feedback.

### Week 6 – Simulation & Competitions

- 3-Day Intensive Company Simulation: apply learnings to solve entrepreneur’s real problem.

- Community project competitions (national → international).

- Final reflection webinar & evaluation.

The virtual company provides a weekly structured experience in form of a continuous/progressive learning lab and acts as a scaffolded practice environment, where inputs feed directly into practice and the final simulation is the culminating challenge. The final simulation builds on company play outputs, adding realism and urgency